## Slide 1
Quality Control for Media
Digitization Projects
Mike Casey
Director of Technical Operations
Darrell Myers
Post Production and Quality Control Specialist
Media Digitization and Preservation Initiative
Indiana University
Blog: http://blogs.iu.edu/mdpi/

## Slide 2: MDPI Overview
Digitally preserve all significant audio and video
Complete by IU Bicentennial in 2020
University-wide initiative
Film began in 2017

## Slide 3: MDPI Goal
Digitally preserve 280,000 audio and video recordings in 3-4 years
Progress:
306,704 digitized as of this morning

## Slide 4: Day of… realization enlightenment reckoning despair dismay doubt dread anxiety horror

## Slide 5: MDPI Overview
At project peak--
600+ objects digitized/day
3,800 digital files/day
12 TB/day

## Slide 6: MDPI Overview
IU scenario
Two digitization units
  Memnon—high throughput parallel transfers (some 1:1)
  IUMDS—1:1 or 2:1
Content from 80+ units
Parallel transfers for 85%
~290,000 recordings digitized in first 3 years

## Slide 7: MDPI Overview
IU scenario
QC Resources
  1 FTE 100%
  1 FTE ~50%
  1 FTE ~20%
  2 student hourlies
  Do we need a QC program?

## Slide 8: Quality Control and Quality Assurance
All vendors make mistakes
All in-house digitizers make mistakes

## Slide 9: Quality Control and Quality Assurance
All vendors make mistakes
Errors should be few and far between
QC/QA system that provides a reasonable
chance of finding or preventing errors

## Slide 10: Quality Control and Quality Assurance
QC
Make certain or verify
Reactive
Product oriented – checking products
Adherence to a defined set of criteria or requirements
(American Society for Quality)

## Slide 11: Quality Control and Quality Assurance
QA
Provides confidence
Proactive
Process oriented
Activities that ensure spec will be met
Part of system planning and design

## Slide 12: Quality Control and Quality Assurance
QA Areas
Personnel
Equipment
Techniques
Practices
Documentation

## Slide 13: Quality Control and Quality Assurance
QC
Critical for clients (institutions)
Performing due diligence
Confirm that digitization products are preservation-worthy (meet defined specification)
80% effective at best (QC for QC?)

## Slide 14: Quality Control and Quality Assurance
QA
Critical for vendors
Can’t rely on inspection for quality
Continual improvement of the system
Identify systemic problems and places for improvement

## Slide 15: Quality Control
Types of QC
1. Automated (Machine-based)
2. Manual (Human-intensive)

## Slide 16: Quality Control
Types of QC
Machine-based – software tools
Commercial and open source

## Slide 17: Quality Control
Types of QC
Machine-based – software tools
In-house scripts
[2017-04-14 18:22:13] [Xcoder:xcode-03:process_objects] Object 45000000242963 state
change: delivery_notify -> in_qc; Object is being checked
[2017-04-14 18:22:14] [Xcoder:xcode-03:process_objects] Object 45000000242963 state
change: in_qc -> failed; Object has failed Auto QC checks
pres/01: Cannot instantiate ffprobe object on
/srv/scratch/transcoder_workspace_xcode-03_prod//MDPI_45000000242963.20170414-174405/data/MDPI_45000000242963_01_pres.mkv. Corrupted?
[2018-04-04 02:47:28] [Xcoder:xcode-02:process_objects] Object 45000000220183 state change: in_qc -> failed;
Object has failed Auto QC checks
mezz/01: Expected 4 for number of audio streams(format:default) but got 1 instead.
mezz/01: Expected 1 for audio channels(audio:0) but got 2 instead.
pres/01: Expected 4 for number of audio streams(format:default) but got 1 instead.
pres/01: Expected 1 for audio channels(audio:0) but got 2 instead.

## Slide 18: Quality Control
Types of QC
Human-intensive
  Relies on human senses
  Characteristics not assessed well by machines
    Reversed audio, changes in speed
    Metadata mixup—content does not match title
    Metadata value is logical but incorrect
QC—It takes a person…

## Slide 19: Quality Control
Human-intensive QC
Without source recording
Direct– compare source recording with file

## Slide 20: Quality Control
Selection for QC
Value-based
More valuable = more resources

## Slide 21: Quality Control
Selection for QC
Risk-based—by risks of a specific workflow

## Slide 22: Quality Control
Risk-based QC
Anything new—format, personnel, equipment, procedures
Anything that changes/ stops and resumes
Certain formats
Workflow specifics

## Slide 23: Quality Control
Quality control as risk management
Risk is the chance of a loss
Risk in digitization—files do not meet spec for preservation

## Slide 24: Quality Control
Quality control as risk management
There is a risk that…
there are digitization errors (loss of accuracy)
it could be done better (loss of accuracy)
there are metadata errors (loss of context and interpretability)
it was not done at all (loss of preservation)

## Slide 25: Quality Control
Quality control as risk management
Impact
  Errors--researchers use inaccurate representations
  Done better--lower quality representations
  Metadata errors—incorrect judgments
  Content not preserved

## Slide 26: Quality Control
Quality control as risk management
Typical risk response strategies
  Reduce risks
  Avoid risks
  Transfer risks
  Accept risks

## Slide 27: Quality Control
IU scenario
Memnon—own robust QC and QA programs
Not part of this presentation
IU understanding partly retrospective

## Slide 28: Quality Control
IU scenario
Reduce or mitigate risk
  Fragile formats (cylinders, lacquers) go to IUMDS 1:1 workflow
    QA function

## Slide 29: Quality Control
IU scenario
Reduce or mitigate risk
    Human-intensive QC—random 10%
    Direct QC
    Retrospective QC program

## Slide 30: Quality Control
IU scenario
Reduce or mitigate risk
Selection criteria for QC efficiency
  Risk-based QC
    Open reel audio azimuth adjustment—Direct QC
    Complexity of formats—LP vs Open reel audio
    More complex = more resources

## Slide 31: Quality Control
IU scenario
Reduce or mitigate risk
Selection criteria for QC efficiency
  Value-based QC
    LPs and 45s
    Stakeholder assessments
    Lower value = fewer resources
      LPs—1.6% checked
      45s—1.8%
      CD-R—3.6%

## Slide 32: Quality Control
IU scenario
Avoid risk
Automated machine-based QC
    Post-processing system developed by IU Libraries
    Checks all files
    ~0% chance of error

## Slide 33: Quality Control
Packager app
Script that runs on local capture machine
Set to run every evening
Acts on files created during the day
Embeds metadata
Creates derivatives

## Slide 34: Quality Control
Packager app QC
Stops if digiprov including signal chain and settings metadata is missing
Stops if any of the following are missing: format, unit, barcode, IARL, ICMT, and BEXT

## Slide 35: Quality Control
Post-processing system QC
Confirm directory is named MDPI_<barcode>
Confirm all file names begin with MDPI_<barcode>
Parse XML manifest
Confirm expected file types for format—pres, prod, mezz, presInt, access
Check for extra files not in manifest
Check for extra files in manifest not in delivery
Verify checksums
Verify file extension for file type is as expected

## Slide 36: Quality Control
Post-processing system QC for audio
Confirm file extension–.wav
Check audio stream count
Confirm sample rate, bit depth, codec name, channels
Compare duration of preservation master and all derivatives

## Slide 37: Quality Control
Post-processing system QC for video
Confirm format and wrapper
Check audio stream count, video stream count, duration of streams
Confirm sample rate, bit depth, codec name, channels for audio streams
Check codec name, width, height
Confirm frame rate
Confirm pixel format YUV 4:2:2
Duration checks across streams (audio, video) and across file types

## Slide 38: Quality Control
IU scenario
Transfer risk
Classic example—insurance
Digitization—vendor contract
Time period for free re-digitization
40 days audio/30 days video

## Slide 39: Parallel Transfer Workflows
Accept risk
38,000 open reel audio tapes
1950s-1990s
Jacobs School of Music
Recitals and concerts
Famous and prominent classical and jazz musicians interspersed
Most of moderate value

## Slide 40: Parallel Transfer Workflows
Accept risk
Parallel transfer or 1:1 digitization?
1:1 workflow = 27.86 Years
4:1 workflow = 7.43 years

## Slide 41: Quality Control
IU scenario
Procedures and tools

## Slide 42: MDPI QC Workflow

## Slide 43: Quality Control
Targets
Imagined – 10%
Actual to date—11.5%

## Slide 47: Tools: MediaInfo

## Slide 48: Tools: WaveLab

## Slide 49: Waveform: DATs

## Slide 50: Tools: QCTools (Clogged Head)

## Slide 51: MDPI QC Workflow
What is our job?
Tedious work
Not just find errors
Validate that files meet preservation spec

## Slide 52: MDPI QC Workflow
What have we found?
29,984 recordings human-intensive QC
Very few problems overall--0.7% failed by IU QC
Most issues found are in metadata, particularly comments
45% of 0.7% failed resulted in re-digitization

## Slide 53: MDPI QC Workflow
What have we found?
A few reversed audio issues
Some variable speed issues
A few azimuth adjustment issues
Several problems with machines
Low video levels

## Slide 54: MDPI QC Workflow
Issues:
QC Specialist sends note to list
The following VHS file has failed IU QC:
40000001522970
This file has failed for the following reason:
40000001522970: Overall blue hue throughout duration.
Adam Nickel
Processing and Quality Control Specialist
Media Digitization and Preservation Initiative - Indiana University
https://mdpi.iu.edu/

## Slide 55: MDPI QC Workflow
Issues:
Memnon invokes CCC procedure
  Containment
  Cause
  Corrective Actions
  Opportunities for improvement of system

## Slide 56: MDPI QC Workflow
Issue: VHS: 40000001522970: Overall blue hue throughout duration.
Containment:
VHS-004 (SN: K6TC00005) was determined to be the source of this issue, machine was replaced. Researched all tapes transferred on this machine to determine when issue started 11/30 - 12/5, resulting in (41) tapes being re-digitized.
Cause: Unsure of specific player defect resulting in blue tint.
Corrective Actions:
Tape machine serviced.
All (41) tapes with blue tint have been redigitized

## Slide 57: MDPI2: Film Digitization

## Slide 58: MDPI2: Project Overview
30,000+ of 100,000+ Reels
Within 3.5 years
Digitization done by Memnon using Laser Graphics Scanstation

## Slide 59: MDPI2: Project Overview
Reels provided by:
  Archives of African American Music and Culture
  Archives of Traditional Music
  Black Film Center/Archive
  IU Libraries Moving Image Archive
  Kinsey Institute
  Lilly Library
  University Archives
  University Athletics
  Regional Campus Archives

## Slide 60: MDPI2: Project Overview
IU Libraries Moving Image Archive (IULMIA)
Coordination with collection holders
Knowledge and research of collections
Best copy selection
Film Preparation/Returns
Works closely with QC Team

## Slide 61: Quality Control Needs - Film
Submission Package QC
  Handle Up to 27TB per Day
Image and Sound QC
  100% Mezzanines
  10% Preservation Masters
  < 16 hrs content / day
Fast Identification, Communication & Reporting for Potential Failures
Overscan DPX + Broadcast Wave in a Tarball
Overscan ProRes 4444
Crop / Color Corrected ProRes 4444
Scanner Project File (.cdir)
Technical & Digital Provenance Metadata (XML)

## Slide 62: Submission Package QC – IU Library IT Build
Package Structure
Checksums
File Naming Conventions
Valid Bag
Correct # of DPX Frames
Compare Deliverables to XML:
- Durations - Codec
- Bit Rate - Frame Rate
- Color Space - Height x Width
- # A/V Channels - Pixel Format
Fully automated QC confirming ….
Notes: XML = Technical and Digital Provenance Metadata

## Slide 63: Submission Package QC – IU Library IT Build
Fully automated QC confirming ….
Notes: XML = Technical and Digital Provenance Metadata

## Slide 64: Image and Sound QC Approaches for Scanned Film
Full Manual QC
  Watch scanned film from begin to end
  Extremely time/cost intensive and exhausting
Spot-Checking
  Play/check only a few spots of scanned film
  Fast, but missing issues in between
Semi-Automated QC (VidiCert)
  Analyze scanned film from begin to end, suspicious sections found are verified by human
  Fast and full temporal QC coverage

## Slide 65: Film QC Workflow
Scanning Operations
  2 scanners, two 8 hr shifts per scanner per day
  Creating up to 4 hrs of content per shift = up to 16 hrs of content per day
QC Operations
  2 FT QC Specialists
  QC of overscan and crop version = up to 32hrs of QC content per day
  3 VidiCert Analyzers, 2 VidiCert Summary stations
  Current QC throughput: ~50 files = 15 hrs per person in a 8 hours shift
Notes: MPDI ….. Media Digitization & Preservation Initiative

## Slide 66: Film QC Workflow
Notes: MPDI ….. Media Digitization & Preservation Initiative

## Slide 67: Film QC Workflow
Notes: MPDI ….. Media Digitization & Preservation Initiative

## Slide 68: Image and Sound QC
Confirm – Preservation Overscan
  Completeness
  No Image / Audio Loss
  No Image / Audio Corruption
  Playback Speed
  Film Prepared well for Scanning
  Faithful Representation of Original
Confirm – Access Copy (Cropped)
  Minimal Frame Lines
  Acceptable Color Correction for Dye Faded Stocks
Create QC Report
Notes: All films – 5-10 mins to QC regardless of duration
Higher importance titles/elements 15 -20 mins to QC
VidiCert’s automatic filters help us be smarter about which portions of the film to investigate instead of random spot checking.
Use automatic defects and graphs to investigate areas of high dust or suspected blur. Some false positives for printed in errors and things like water or birds flying misinterpreted as dust.
Postpone questionable films for group reviews
Access Copy – As for quick viewable copy for streaming to get content up quickly. Not perfect but improved for ease of viewing. Any title identified as high importance after the fact can be selected for further preservation/restoration work.

## Slide 69: Image and Sound QC Automated Defect Detection Functions
Gamut/Clipping (Under & Over Exposure)
Freeze Frame
Framing Error
Dust/Dirt/Hair Level
Film Grain Noise Level
Out of Focus / Blurriness Level

## Slide 70: Image and Sound QC Automated Defect Detection Functions
Contrast/Luminance Range
Black & Single Colored Frames
Black Bar / Aspect Ratio
Macroblocking
Audio Silence, Loudness, Superimposed Sound

## Slide 71: Image and Sound QC Interactive Defect Verification
Advanced summarization and navigation by various timeline based defect and quality measure views
Full featured desktop player: zoom, field split, time accurate playback, second monitor full screen, selectable audio channels
Fully customizable user interface with presets

## Slide 72: Image and Sound QC Stripe Image
Image Loss & Framing
Faded Stock – Color Correction Needed

## Slide 73: Image and Sound QC Identified Defects
Crushing / Clipping
Added Tones
Foreign Object in Frame
Dirt / Dust
Notes: An example of how errors can creep up suddenly…
VidiCert Gamut & Luma Error detection greatly improves our speed to identify this error – 7 in July, 19 in August, 2 in September
Helped identify quickly a new element group of negatives that were creating crushing in scans unlike other negatives.
Dust and focus filters create graphs to help us pinpoint sections of film to quickly spot check.
Audio Spectrum helps us check for audio loss and introductions of tones, which we had early on. This led to the scanner manufacturer updating their optical reader.

## Slide 74: Image and Sound QC Identified Defects
Dropped Audio Samples
(Interstitial Type Errors)
Caused by Film Instability
Identified in iZotope RX
Fixed with R&D/Software Updates
A/V Sync Issues
Caused by Shrunken Film
Identified by QC Specialist
Developed Manual “Sync. Test”
Fixed with R&D/Software Update

## Slide 75: Image and Sound QC Identified Issues
Da Vinci Resolve
Verify Playback Speed (FPS)
RGB Levels
Side by Side Comparisons

## Slide 76: Reporting

## Slide 77: Reporting and Tracking

## Slide 78: Image and Sound QC What have we done?
Human-intensive QC
  December 2017 – October 2018
  7,883 titles (15,766 files)
  Average file duration: 16 Min. 06 Sec.

## Slide 79: Image and Sound QC What have we learned? (from QC or affecting QC)
Challenges
  Unusually heavy use of scanners in two scanner workflow over two shifts per day
  Maximize both quality and speed
  Various hardware and software issues to work through
  Need to engage in R&D while doing production

## Slide 80: Image and Sound QC What have we learned?
Challenges
  Re-start at beginning of project
  Cleaner failure
  Human error (expected)
    Incorrect scanner settings
    Excess dirt on film
    Stabilization problems on films with physical issues

## Slide 81: Image and Sound QC What have we learned?
QC program
  Identified audio and image issues
  Fed data into R&D process
  Grew better with experience (learning curve)
  Helped vendor become more accurate

## Slide 82: Image and Sound QC Most Critical Issues & Effectiveness
Chart: Verified defects per File in Files to be Re-Scanned and Files to be Archived
| Dirt | Gamut/Clipping | Crackle | Framing Errors | Colour Grading Problems | Film Hair | Film Unsteadiness | Dust/Hair/Bacteria | Silence | Luma Range Error | Splice Bump | Dirty Splice | Click/Pop | Black Frame | Colour Shift | Video Frame Rate | Geometric Distortions | Under-Exposition | Audio Level Variations | Glitch | Blur | AV Synchronisation Problems | Descriptive Metadata | Visual Defect | Freeze Frame | Noise | Over-Exposition | Visible Scotch-Tape Cut Edition or Repair | Color Mismatch | Gelatin Loss | High Frequency Tone | Severe Emulsion Loss | Wow
To be Archived | 0.038958 | 0.077836 | 0.11632 | 0.033301 | 0.0064532 | 0.013464 | 0.030513 | 0.0051785 | 0.18762 | 0.0034257 | 0.014181 | 0.0040631 | 7.9669e-05 | 0.064532 | 0.00023901 | 0.00015934 | 0.00039834 | 0 | 0.0011154 | 0.00087635 | 0.00079669 | 0 | 0 | 0 | 0.00023901 | 0 | 0 | 0 | 7.9669e-05 | 0.00023901 | 7.9669e-05 | 0.0012747 | 0.00015934
To be Re-Scanned | 0.69831 | 0.55462 | 0.5 | 0.37744 | 0.21814 | 0.20904 | 0.17263 | 0.16743 | 0.10403 | 0.056892 | 0.027308 | 0.024707 | 0.01593 | 0.013654 | 0.011053 | 0.0084525 | 0.0058518 | 0.0048765 | 0.0026008 | 0.0019506 | 0.0013004 | 0.00097529 | 0.0006502 | 0.0006502 | 0.0003251 | 0.0003251 | 0.0003251 | 0.0003251 | 0 | 0 | 0 | 0 | 0
QC allows to detect defects -> Files „To be Re-Scanned“
QC+Re-Scan reduces the total defects rate per file from 3.2 to 0.6 ->More than 5 times less issues (Archived vs. Re-scanned)

## Slide 83: MDPI Operations Overview Re-Scans per Month
Chart: #Archived and #Re-Scanned Files
| 201712 | 201801 | 201802 | 201803 | 201804 | 201805 | 201806 | 201807 | 201808
Archived | 417 | 998 | 1597 | 2142 | 1927 | 1294 | 1892 | 927 | 1242
Re-Scanned | 51 | 206 | 282 | 876 | 224 | 108 | 253 | 890 | 182
Goal of QC is to drive down rescans - September rescans down to 6%
IU requests some rescans for reasons other than defects
Requirements and complexity change for some collections and film stock
Scanner and Film Cleaner equipment issues led to spikes in March and July
  Were detected and solved
Notes: 03/18 Optical reader changed to image based sound reader, this introduced interstitial errors (e.g. pops) in the beginning (software has been revised)
07/18 Scanner of new negative stock (crushing in the whites) produced crushing in the darks (in the positive)
07/18 Film Cleaner Problem

## Slide 84: Conclusions…
Approach to QC is a project strength
  Allows IU to better understand its diverse collections and adapt workflows
  Enables high quality archive package
Submission Package QC
  Ensures packages meets archiving standards

## Slide 85: Conclusions…
VidiCert Image and Sound QC
  Integrates very well with IU workflow and Submission Package QC
  Systemic issues can be detected quickly
  Detailed automatic and interactive detection functions helps greatly in finding the origin of an issue
Strengthens our relationship with Memnon

## Slide 86: MDPI QC Workflow
The big picture:
Preserve for long period of time
Humans make mistakes
Validate content meets preservation spec
Correct errors
Understand risks—mitigate or accept
Provide access to quality content produced by quality digitization system

## Slide 87
Things of Quality Have No Fear of Time
--Author unknown

## Slide 88
Quality Control for Media
Digitization Projects
Mike Casey (micasey@indiana.edu)
Director of Technical Operations
Darrell Myers (dsmyers@indiana.edu)
Post Production and Quality Control Specialist
Indiana University MDPI
Blog: http://blogs.iu.edu/mdpi/
“Things of Quality Have No Fear of Time”